OPERATIONAL PLANNING WORKSHEET

Organization name:_LIN Center for Community Development

List a few examples of goals that your organization wants to meet. These can be goals set through a formal strategic planning process,  or they may be other goals that your organization has established in another way.

1. Launch a social enterprise to support our not-for-profit activities. 2. Get information to NPO partners and prospective partners who do not have e-mail/Internet access. 3. Attract more NPO partners.

List a few examples of requirements with which your organization must comply.  These can be external requirements, such as government regulations.  Or they may be internal requirements for your organization.

1. Create project income/expense reports and update them for all staff on a bi-monthly basis. 2.Provide mid-term and end-of-year reports to VUSTA. 3. Improve the relationship between LIN and local government agencies responsible for overseeing our programs and activities.

Now please select a goal or a requirement that you would like to work with during today’s seminar:

The goal or requirement I will work with today is: GOAL: Get information to NPO partners and prospective partners who do not have e-mail/Internet access.

Goal or requirement: Get information to NPO partners and prospective partners who do not have e-mail/Internet access.

Step 1:  CLARIFY THE GOAL OR REQUIREMENT

Additional information about this goal or requirement that will help clarify what needs to be achieved. Much of LIN’s communication and information sharing activities occur on email, our website and social media platforms. We use these platforms to minimize costs and make efficient use of staff time. However, we believe that at least 10 to 15% of our partners and prospective partners do not have regular or reliable access to the Internet or email. As a result, we are underserving our beneficiaries and we are prevented from reaching prospective beneficiaries.

Step 2:  UNDERSTAND THE CURRENT SITUATION

| Has your organization started working on this goal/requirement? If so, what have you accomplished to date? | Yes We used to print and mail hard copies of our event fliers and invitations. We make calls to NPOs we suspect do not have regular email access. We explored the possibility of publishing info in print media (too expensive). |
| --- | --- |
| Is there a date by which this goal/requirement must be met? If so , when? | On-going |
| What are the barriers to achieving the goal/meeting the requirement? | 10 to 15% of our NPO partners and prospective NPO partners do not have regular or reliable access to email/Internet Publishing announcements through the media is expensive. Printing and mailing announcements is time-consuming and expensive. |
| Who within your organization should be involved in working to achieve this goal/meet this requirement? | Son – NPO Liaison Members of the Program Committee, a sub-committee of the LIN Board of Directors |
| Other important information to understand about the current situation. | NA |

Step 3:  IDENTIFY AND EVALUATE POSSIBLE APPROACHES FOR MEETING THE GOAL/COMPLYING WITH THE REQUIREMENT

Possible approaches that could be used to meet the goal/comply with the requirement: Develop a volunteer network to help us reach out to the NPOs without email/Internet access. Print fliers/event announcements and distribute them by mail and/or at events that are attended by our partners and/or prospective partners. LIN staff can help NPOs to gain/improve their access to email/Internet. LIN staff can make calls to NPOs without email/Internet access.

Select an approach to work with for the remainder of this seminar.

Selected approach: A combination of approaches 1 & 4 – Develop a call system, involving LIN volunteers, to reach out to our NPO partners and prospective partners without email/Internet access.

Step 4:  Identify steps for carrying out the selected approach  (complete Columns 1 and 2)

Step 5:  Develop timeline and make assignments (complete columns 3, 4, and 5)

| Column 1 | Column 2 | Column 3 | Column 4 | Column 5 |
| --- | --- | --- | --- | --- |
| Task # | Task description | Assigned to | Start date | End Date |
| 1 | Make a list of NPOs who do not have email or who do not use email regularly | Son | July 11 | July 18 |
| 2 | Design a contact system and determine how many volunteers are needed to quickly contact all NPOs on the list from task #1. | Son/Program Committee | July 18 | July 25 |
| 3 | Draft a Volunteer Job Description | Son/PC | July 25 | July 27 |
| 4 | Recruit Volunteers | Truc | July 27 | August 10 |
| 5 | Provide training and orientation for volunteers, select a volunteer leader for coordination | Son | August 12 | August 12 |
| 6 | Write a script for Volunteers and develop a record-keeping system for volunteers, prior to calls | Son | August 13 | August 20 |
| 7 | Test the system after each round of contact | All | On-going | On-going |
| 8 | Reflect on the system – success and challenges – suggest improvements | All | On-going | On-going |
| 9 | Refine the contact system | Son/Volunteer Lead | On-going | On-going |
| 10 | Reflect and improve every 6 months | Son/Volunteer Lead | Every 6 months | Every 6 months |

Step 6:  Monitor progress

| Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 |
| --- | --- | --- | --- | --- | --- |
| Task # | Task description | Who will report progress? | Format for reporting progress | When will reports be required? | Who will receive progress reports? |
| 1,2,3,6 | Design the contact system | Son | Report to Program Committee describing the contact system | July 25 | PC |
| 4,5 | Recruit and train volunteers | Truc | Initial report, to Program Committee followed by quarterly updates on volunteer status. | August 12 | PC |
| 7-10 | Evaluate the program and recommend improvements as appropriate. | Son | Report to Program Committee after 6 months of operation, and every 6 months thereafter. | Mid-Sept and every 6 months thereafter | PC |

Step 7:  Measure success

| Goal/requirement: | Get information to NPO partners and prospective partners who do not have e-mail/Internet access. |
| --- | --- |
| Approach : | Develop a call system, involving LIN volunteers, to reach out to our NPO partners and prospective partners without email/Internet access. |
| How will we know if this approach was successful? What will have happened? By when? | Increased attendance by NPO Partners and Prospective Partners without emails or limited email usage. Goal is an average increase of 2 NPO partners or prospective partners without e-mail per event (compared with average attendance levels in the year prior to establishing the phone network). New Partners connected to LIN through the Volunteer network. Goal is addition of 3 new partners without e-mail by December 31, 2011. |
| Who is responsible for measuring and reporting success? | Son |
| What is the format for the report? | Description of the system and any improvements made, update on success measures. |
| Who will receive the report and what will they do with it? | Program Committee, LIN Board of Directors If success is being achieved, nothing will be done. If there are challenges, the PC may recommend another approach. |